## PlannerV1.5
Project Name | Budfie | Project PlannerV1.5
Document Version | Project Planner V1.5
Client Name | Aarushi & Venu
Project Manager | Ashish Singh
Project Coordinator | Harshit Goel
Technology Stack | App : Native ; Backend : PHP
Deliverables | iOS App, Android App, Admin Panel.
Activity | Features | Responsible Team | Delivery Date
Milestone 1
Aplication Designs
App Flow & Designs | Logo | Designer | 2017-11-23
| Splash Screen | Designer
| Login Flow | Designer
| Profile Setup | Designer
| Interest Page Screens(2) | Designer
| Landing Screen | Designer
| Greting Landing Page | Designer
| Event flow including inviting friends and Adding greeting landing Page. | Designer
Milestone 2
Aplication Development |  |  | 2017-12-18
Splash | Splash Screen | App Developer & Backend Developer
Login and Signup Screen | Social Signup-Facebook and Google, Budfie Sign In | App Developer & Backend Developer
| Phone No Screen | App Developer & Backend Developer
| OTP Screen | App Developer & Backend Developer
Profile Setup Screen | Enter name, change Pic, Enter Date of Birth, Social Integration(Facebook and Google) | App Developer & Backend Developer
interest Preference Screen | Sports interest , Movie Interest, TV series Interest.(UI) | App Developer & Backend Developer
Interest Screen 2 | Intrest screen 2 as per the design | App Developer & Backend Developer
Thank You Screen | Thank you screen 3 sec | App Developer & Backend Developer
Landing Screen | Landing Screen UI | App Developer & Backend Developer
Event Screen | Event Screen (UI only) | App Developer & Backend Developer
| Creat personal events | App Developer & Backend Developer
congrats screen | congrats screen | App Developer & Backend Developer
Aplication Designs(Rest Designs)
App Flow & Designs | Holiday Planner | Designer
| Greeting Flow | Designer
| Chat Flow Complete excluding GIFS | Designer
| Setting Screen | Designer
| Edit Profile Screen | Designer
| Favrouite Screen | Designer
| invitaiton screen | Designer
| Time Out Flow | Designer
Testing and correction |  | Tester & developers
Milestone 3
Edit Profile | Side Menu-> Edit Profile as per the designs | App Developer & Backend Developer | 2018-01-12
Edit Events |  | App Developer & Backend Developer
Event Detail page | Created or invited event detail page | App Developer & Backend Developer
Invite in app users | User will able to invite friends within app and though phone contacts. | App Developer & Backend Developer
Invitation screen | Acceptance or rejecting the events invitation. | App Developer & Backend Developer
Movie and Series tab | Complete UI with API integration (Client API) | App Developer & Backend Developer
Sports Tab | Complete UI with API integration (Client API) | App Developer & Backend Developer
phone event tab | Compete UI of phone tab and API integration | App Developer & Backend Developer
Concert event tab | Complete UI with Events high integration API
More screen | More screen UI with Edit and View profile funcationality. | App Developer & Backend Developer
Time out flow | Landing screen UI with functional Mood system | App Developer & Backend Developer
Designs Changes
Pending Screens | Greeting flow, Holiday Planner, more screen, chat screens (Excluding Face in hole, emojis, GIFs, popup and 3d card) | Designer
Admin
User Management | All the registered users will be listed, searched, view history and Admin can block and unblock any user. | App Developer & Backend Developer
Events Management | All the events of the app will be listed user wise and admin can view or block or unblock them. | App Developer & Backend Developer
Testing and correction |  | Tester & developers
Milestone 4
Time out flow | Api integration for every rated smiley. | App Developer & Backend Developer | 2018-02-12
Time out flow | News API integration (Client API) | App Developer & Backend Developer
Time out flow | Movie Listing | App Developer & Backend Developer
Events Sports TAB | Cricket Detail Screen UI + API integration | App Developer & Backend Developer
Holiday Planner | Detailed Holiday list of the selected month as per the deisgns. | App Developer & Backend Developer
Greeting flow | Complete UI with API integrations | App Developer & Backend Developer
Greeting flow | Shared, Received and Drafted Greetings UI and API integrated | App Developer & Backend Developer
Greeting flow | Editable Greeting from Draft and Shared managed Localy | App Developer & Backend Developer
Greeting flow | sound card customization with the client shared audio clips (Audio clip and cards content needs to be shared by client) | App Developer & Backend Developer
Greeting flow | face in a whole | App Developer & Backend Developer
Customization of calender throughout | Customization of calender throughout | App Developer & Backend Developer
Testing and correction |  | Tester & developers
Milestone 5
Holiday Planner | Form as per the design (Client API) | App Developer & Backend Developer
Time out flow | HAPPY: Game Winit, Shop , Plan Long weekend SAD: Funny Clips, Happy Thoughts , Jokes MAD: Calm Music, Game Killit , Funny Clips BORED: Both Games, News , Funny Clips | App Developer & Backend Developer
Greeting flow | Customizing the GIFs and shae it with in app and through deep linking. (Gifs needs to be shared by client) | App Developer & Backend Developer
Events Sports TAB | Tennis and Batminton routing via Admin. | App Developer & Backend Developer
chat Screen | Complete chat screen UI | App Developer & Backend Developer
Chat screen | Contact List of in App users | App Developer & Backend Developer
Chat screen | create group, group and individual chat. | App Developer & Backend Developer
Chat sceen | Chat socket implementation with emojis, stickers and audio clip. | App Developer & Backend Developer
Notifications | Complete set of push notifications. | App Developer & Backend Developer
Settings | Complete UI with API integration | App Developer & Backend Developer
Gifting (Out of scope) | Discussion pending.
Admin
Time oout Management | Admin will able to add, delete, active and inactive the gifs, sound, thoughts, jokes and funny videos | Backend Developer
Greeting managemnet | Admin will able to add or delete the gifs or active inactive | Backend Developer
Holiday List Management | Admin will able to list the past holiday, location visted date and all the basic details | Backend Developer
Notifications | Admin will able to send notification to all the Budfie users. | Backend Developer
Adding sports from Admin Tennis & Badminton | Admin will manually able to add sports data from backend. Change Request | Backend Developer
Shop-a-gram or Gifting (Out of scope) | Needs discussion
Testing and correction |  | Tester & developers
UAT and Making App Live submission 5th March
Note* We have not included Games and Shopagram functionality on this as it is still under discussion we will share the revised milestone plan with revised dates once we close the discussions.

## Requirements
Clients Dependencies: | Modules
Content Events Categoies. | Event Module
Content of Emojis, face in hole and Pop 3 D card. | Greeting Card
SMS gateway | Sign In and Change Number | Insufficient Credits
Movie/Series API | Event Module | Routing via Admin completely (change Request)
Sports API | Event Module | Cricket and football we have got rest needs to be managed by Admin (Change Request)
Holiday Planner API | Holiday Planner Module | Roouting via admin in terms of holiday dates.
Social Login Accounts | Sign In and Change Number and Events Module | We need to have a change facebook account in which client personal account should be synced.
Domain name | Admin
AWS server details | Admin and API
Developers account (iOs and Android) | iOS and Android making live